## Pending
New Point No. | Original Point No. | Description | Communication Made | Functional Issue(y/n) | Typo Error | Ease of doing | Panels | Remarks Vivek | Remarks Me
1 | 3 | Admin Panel - > Seller Bidding - > Bid delete option to be there after buyer selects that bid but before awarding. This is required since, if some issue is found with seller whom buyer has selected, admin might need to delete bids made by him, so that buyer can select bids made by other people. In the absence of it, the entire bidding exercise will be required to be done again. Alternatively, Admin should have option to Select another offer posted by another Seller before awarding the order. Required since if any seller misrepresent the facts or is disqualified for some reason and cannot supply post bidding, admin should be able to change. |  | y |  | 1 | Admin Panel | Completed | Pending - Awarded bid should not be Deleted. Only in process to be Deleted. Currently even awarded bids are also getting deleted.
2 | 8 | Admin should have the access to edit or delete buyer order before activating it for bidding including editing the attachment. This is still not there. | Yes, 16/8/25 | y |  | 2 | Admin Panel | Completed | Pending
3 | 15 | Admin Panel - When the order is awarded, the message what comes in is, "Auction end time" and "status updated successfully" instead it should come as "Order awarded successfully". Also the message doesn’t go away it remains on the screen. It should go away after sometime |  | Y |  | 1 | Admin Panel | Need to talk | Pending
4 | 18 | Whatsapp integeration also required |  | y |  | 3 | Buyer and Seller Panel Both | Need to talk | Additional Development
5 | 19 | In Buyer Panel -> Select Bid -> after bid selection, 'bid activated' is shown, to change it to "Bid Selected Successfully' in a green bar. | Yes, 13/8/25 | n | y | 1 | Buyer Panel | Completed | Pending
6 | 22 | Whenever buyer add description or additional information of impurity/Products, the large description should also have formatting - like bold letters, para, etc |  | n |  | 1 | Buyer Panel | Completed | Pending
7 | 23 | Dashboard need to be updated Buyer, seller and admin |  | Y |  | 3 | All 3 Panels | No Remarks | Dashboard template already shared
8 | 25 | Seller Panel - > My Biddings - > 4 options to be there under 'Status' field (a) 'Awarded' in green background - for order awarded to this seller, (b) 'In Process' - in orange background - if the order is not yet awarded to any one, (c) 'Missed' - in light red background - If the order is awarded to anyone else, and (d) 'Cancelled' - in light grey background - if the bid itself is cancelled by Admin |  | n |  |  | Seller Panel | Partiallly done
9 | 28 | In Buyer Signup Page, when duplicate values are inserted in a field, it should be highlighted then and there and not after submitting the page |  | Y |  |  | Buyer Panel | Designer Work | Pending
10 | 30 | Even after the admin cancels an order, the customer can still select an offer. Once the customer selects a new offer, the order status changes from "Cancelled" to "Admin to Confirm" on the customer side, and to "Pending Confirmation" in the admin panel. | Yes,12/08/25 | Y |  |  | Admin Panel | Completed | Pending to be done
11 | 33 | Seller approvals and certifications to be recorded in seller profile in given field and option to be given to buyer to see those certifications field before selecting the offer. |  | Y |  |  | Seller Panel | Additional Development | Additional Development
12 | 34 | In the 'Become a Seller' section, email verification is required. When the seller enters their email ID, an OTP will be sent to their Email address for verification. Similarly in the 'Become a Buyer' section, email OTP validation is required. |  | Y |  |  | Buyer Panel | Completed | Error Message as per the screenshot in the right. If duplicate fields are there, it should generate a proper error message
13 | 43 | In Website -> Social Media Links to be defined (facebook, Linkedin, Insta, X Will be provided to you) Facebook: https://www.facebook.com/profile.php?id=61582013601892 Instagram: impurityx_thirdworld_innomart Linked in: https://www.linkedin.com/showcase/impurityx X : @impurityx_1 |  | y |  |  | Buyer and Seller Panel Both | Link not there | Link shared with you earlier, now inserted in details, to be mapped
14 | 53 | Admin Panel - In Overview - only Active buyer and seller count should be displayed in screen like out of 7 buyer only 6 buyer is active the count of 6 should be displayed or else in that box instead of 7+ just state "6 of 7" |  | n |  |  | Admin Panel | Completed | Pending
15 | 58 | Reward Points Integration Required - Details already given long back. When the order is awarded to the seller by admin, the reward points based on defined parameter in admin section, will be created and will show as 'Yet to Allocate' to the Buyer. This will remain till following: a) If order is 'cancelled' for any reason, 'YTA' point will disappear. b) If Order delivery is 'Delivery Accepted' by Buyer, 'Order Concluded' option to be available to Admin in Buyer Order. Admin to Select it to conclude that Order after receiving payment. On Confirmation, Popup to come 'Grant Reward Point (Y/N) :' If 'yes' it will be trasnferred from YTA to Clear Points. |  | Y |  |  | Admin Panel | No Remarks | Additional Development
16 | 66 | Banner size need to be fixed in Mobile view |  | n |  |  | All 3 Panels | Designer Work | Pending
17 | 67 | In Mobil view->Banner Contact us and How it works button comes below as a result we are unable to see that buttons |  | n |  |  | All 3 Panels | Designer Work | Pending
18 | 68 | The subcategories block needs to be updated. Currently, in mobile view, only one block is visible at a time. |  | n |  |  | All 3 Panels | Designer Work | Instead of one green block, it should be 2 blocks appearing together by making each block smaller
19 | 68b | On Mobile - In Seller Panel-> when you click on the top right menu bar (3 horizontal lines), the menu overlaps on the LIVE product which is there on the screen for the bidding. On scrolling the menu up and down, sometimes if goes back of the Live product, sometimes it comes in front of the live product. |  | N |  |  | Seller Panel |  | New Error
20 | 69 | In mobile view, only one product card is currently visible on the screen at a time. Can this be updated to display two product cards side by side within the screen width? That will have better UX |  | n |  |  | All 3 Panels | Designer Work | Pending
21 | 70 | Additionally, when viewing the details of an active bid product on mobile, the product image occupies the half of the screen, requiring users to scroll down to see the product details. Can it be made smaller |  | n |  |  | All 3 Panels | Designer Work | Pending
22 | 75 | In Seller Login / Buyer Login page, Forgotten Passowrd not working. To be activated |  | n |  |  | Buyer and Seller Panel Both | Completed | Pending - Error Message shown - seems of EMAIL issue
23 | 77 | Additionally, when clicking on the My Profile icon, the dropdown menu (containing Action Task, My Profile, and My Notices) currently appears above in mobile screen. The menu should instead appear on the left-hand side, making it easier to access and control the available options. |  | n |  |  | All 3 Panels | Designer Work | Pending
24 | 78 | In Mobile screen - When clicking on the All Products section, a dropdown should appear displaying all available categories. |  | n |  |  | All 3 Panels | Designer Work | Pending
25 | 78a | In Desktop and Mobile - When clicking on the Categories section on Navigation Bar, products with 'Coming Soon' remarks are visible with blank qty etc. It should only show products for which bidding is 'Live' under that specific category, and if no bidding is Live, it should show a message 'There is no open requirements under this category' |  | y |  |  | Seller Panel |  | New Error
26 | 78b | In Desktop and Mobile - When clicking on the Categories section, the menu opens behind the banner and is nor easily visible. |  | N |  |  | Seller Panel |  | New Error
27 | 79 | In mobile - The Home, Categories, and My Profile icons should be displayed at the bottom of the screen for easy access. |  | n |  |  | All 3 Panels | Designer Work | Pending
28 | 80 | In the Admin Panel, there should be an option to define and manage these options. 'Trusted by 500+ businesses', and companies icon upload below it, and 'What clients say' section i.e. Testimonials |  | Y |  |  | Admin Panel | Additional Development | Pending
29 | 81 | There should be a "Reorder" option in the Order History section. If a buyer wants to order the same product again, they shouldn't have to go back to the search bar and raise a new request from scratch. It's time-consuming. With a simple "Reorder" button, they can repeat the same order with just one click - or change whatever they want to in it - much faster and more convenient |  | Y |  |  | Buyer Panel | Completed | Pending. It was shown to me as done, but again the option button is not there.
30 | 82 | In Buyers and Sellers Panel - > When New Notices and Communications are sent, the 'My Notices' tab on the menu should also include some red dot signifying that there are new notices. Same thing for Communications. |  | y |  |  | Buyer and Seller Panel Both | Completed | Notices - Done, Communication - Pending
31 | 82a | In Admin Panel - > When New Communications by Admin is sent to buyers or sellers, it doesn't fetch the order details but throws an error message. |  | Y |  |  | Admin Panel |  | New Error
32 | 89 | Some Email templates still not integrated i.e. While Sellers Bid, mails to go to all earlier bidders, Offer Selections by Buyer – Only if any seller has provided the quote. Email to go to Buyer when Seller change the status to 'Order Initiated', 'Order Completed' , 'Delivery Initiation' and 'Delivery completed'. Email to go to Seller when Buyer accept 'Delivery Acceptance' |  | y |  |  | All 3 Panels | On Live Work | Pending
33 | 91 | How it works-> Section - Why Choose Us - 1st point to be changed from "Buyer-Defined Lead Times & Certifications" to "Streess Outsourced - From Seacrh to Supply" |  | n | Y |  | Buyer Panel | Designer Work | Pending
34 | 93 | Buyer Rejected -There should be an option of Order Rejection to Buyer so that buyer will able to reject the Order raised by him after receiving all bids. If buyer rejects by clicking on reject button the pop up box should be appear stating the reason for rejecting the order. (Buyer will able to reject before selecting the bid once bid selects the reject button should disappear from the screen.) | Same | y |  | 2 | Buyer Panel | Completed | Issue - The rejection reason need to be restricted to 30 characters.
35 | 95 | In Admin Panel -> Users Management -> Buyers and Sellers, we need to show login counts so we can keep track of how many times each user has logged into the dashboard. |  | Y |  |  | Admin Panel | Additional Development | Pending
36 | 97 | If Seller want to download the details of particular order how can he download it, so beside the view and edit icon there should be download option so he can download it. Also when order awarded time the details should also displayed in email |  | n |  |  | Seller Panel | Additional Development | Pending
37 | 98 | In Seller Panel-> When we intiate delivery, along with the Invoice Numbers, Courier Details field should also be there like 'Courier Name: '; 'Tracking ID: '; 'Courier Date: ' |  | n |  | 1 | Seller Panel | Completed | Error - while saving the data, the Courier Detail data doesn’t get saved. Also, Neither invoice details or courier details are available to be seen by Admin or Buyer
38 | 99 | All Loaders to be removed |  | Y |  | 1 | All 3 Panels | Designer Work | Pending
39 | 100 | Buyer Panel -> Request Product Addition - > Text 'Impurity Information' should be changed to 'Product Information' |  | n | Y |  | Buyer Panel |  | New - Only text change
40 | 101 | Downloaded Data template modifications for 'Order Exports' and 'My Biddings' - requested changes yet to be completed - Already Shared on 15th Sep 2025 |  | n |  |  | Buyer and Seller Panel Both |  | Pending
41 | 102 | Updated Transparent Logo to be activated in Buyer and Seller Panel |  | N |  |  | Buyer and Seller Panel Both |  | Pending
42 | 103 | Admin Panel - After Buyer's 'Delivery Acceptance', order should be 'Closed' by admin. Option is there but not working. |  | Y |  |  | Admin Panel |  | Pending